## Slide 1: Scrum management for Group Project

## Slide 2: Wk beginning : 29/01/18
Objectives for the week:
Assess progress on project and improvements/ changes to be made
Finish Watson conversation service by end of next week
Meetings to be held this week:
Initial meeting with group - 30/01/18
Extended group meeting - 01/02/18
Work/ tasks completed this week :
More detailed scrum style planning created for week by week progress
Meetings arranged with sponsor and supervisor

## Slide 3: Wk beginning : 05/02/18
Objectives for the week:
Finish Watson conversation service
Begin designs for website layout
Assess Avatar design
Meetings to be held this week:
Meeting with Gail - 06/02/18
Meeting with John -
Group meetings - 09/02/18
Work/ tasks completed this week :
Watson conversation service

## Slide 4: Wk beginning : 12/02/18
Objectives for the week:
Test Watson conversation.
Look into node.js and how to incorporate conversation into webpage chat box.
Add chat hints and tips to webpage to help users.
Meetings to be held this week:
Meeting with Gail - 13/02/18
Meeting with John - 12/02/18
Group meetings - 15/02/18
Work/ tasks completed this week :
Node.js understood for both webpage
Testing of conversation service complete
Help information added to webpage

## Slide 5: Wk beginning : 19/02/18
Objectives for the week:
Begin work on speech to text and text to speech services
Continue integrating conversation into webpage
Add small amounts of animation to the avatar
Meetings to be held this week:
Work/ tasks completed this week :
Encountered issues with text to speech service
Webpage now includes working chat feature
Began animation development

## Slide 6
Wk beginning : 26/02/18
Objectives for the week:
Add small amounts of animation to the avatar
Continue adding blog posts to page
Look into Watson personality service
Test and improve functionality of webpage
Meetings to be held this week:
Meeting with gail - 27/02/18
Work/ tasks completed this week :
Speech to text is not possible to incorporate so have been advised by sponsor to remove feature
Blogs are now up to date with current progress

## Slide 7
Objectives for the week:
Continue working on animation for the avatar
Develop a demo Watson personality service
Develop a demo for text to speech
Work/ tasks completed this week :
Animation fitted to avatar
Personality insights demo created – need way to gather all tweets
Meetings to be held this week:
Meeting with gail - 6/03/18
Wk beginning : 05/03/18

## Slide 8: Wk beginning : 12/03/18
Objectives for the week:
Adding viewing CV functionality to webpage
Develop personality service in node.js
Review avatar animation
Meetings to be held this week:
Meeting with gail - 6/03/18
Meeting with jon -
Group meetings -
Work/ tasks completed this week :

## Slide 9: Easter Break